## Case Study Assumptions
LP | Assumption | Task | Duration
1 | Team of 4 | Introduction
2 | 5 teams | Review Process
3 | Duration 90 minutes. It is important to split activities | Review Inputs
4 | Every team may ask for 3 adivices of PM Governance team | Review Requirements
5 | Issues are hidden, they pop up after 45, 60, 75 minutes after start | Define Scope
6 | PCs for every participant | Define Business Case
7 |  | Distribute Task
8 |  | Identify Risk
9 |  | Plan Schedule
10 |  | Plan Budget
11 |  | Manage Issue #1
12 |  | Manage Issue #2
13 |  | Manage Issue #3
14 |  | Summary
15 |  |  | 0
16
17
18
19
20

## Process
Forecasts
Sales Orders
1. Capacity Planning
3. Production Preparation
2. Material Resource Planning
4.Goods Receiving
6. Material Picking
7. In-house Components Sub-assembly
8. Bus Assembly
5. Quality Control
9. Bus Delivery

## Inputs
Process Cycle per 1 Bus unit
ID | Activity | Duration (h) | FTE | Worktype
1 | Capacity Planning | 2 | 2 | White collar
2 | Material Resource Planning | 4 | 4 | White collar
3 | Production Preparation | 6 | 4 | White collar
4 | Goods Receving | 10 | 5 | Blue collar
5 | Quality Control | 4 | 4 | White collar
6 | Materials Picking | 2 | 8 | Blue collar
7 | In-house Component Sub-assembly | 20 | 8 | Blue collar
8 | Bus Assembly | 16 | 48 | Blue collar
9 | Bus Delivery | 2 | 4 | White collar
Plan manufactured 1000 buses in 2015.
Cost of workload
Blue collar |  | 50 | PLN/H
White collar |  | 200 | PLN/H
Waterfall deployment (Phased) |  | Estimate benchmark
Plan |  | 10%
Analyze |  | 15%
Design |  | 15%
Build (Development) |  | 30%
Test |  | 20%
Deploy |  | 10%
100%
Available IT Team |  | FTE | Cost
Project/Test Manager
Business Analyst
Solution Architect
Developer
Tester

## Requirements
Requirements input
ID | Requirement | Business process | Estimated dev (h) | Value added
1 | Kanban functionality | 6. Materials Picking | 80 | Decrease 1 FTE
2 | EDI Communication | 4. Goods Receiving | 120 | Decrease activity cycle by 3h
3 | EDI Communication | 2. Material Resource Planning | 120 | Decrease 1 FTE
4 | Just In Sequence | 8. Bus Assembly | 160 | Must-have to increase capacity to 2000 units
5 | Just In Sequence | 7. In-house Component Sub-assembly | 80 | Decrease activity cycle by 2h
6 | Manufacturing Execution Dashboards | 8. Bus Assembly | 280 | Must-have to increase capacity to 2000 units
7 | Manufacturing Execution Dashboards | 7. In-house Component Sub-assembly | 80 | Decrase 2 FTE
8 | Two-step picking | 6. Materials Picking | 60 | Decrease 1 FTE
9 | Planning capacity of workstation | 1. Capacity Planning | 30 | Must-have to increase capacity to 2000 units
10 | Bill Of Material Preparation | 3. Production Preparation | 80 | Decrease activity cycle by 1h
11 | Deviations handling | 2. Material Resource Planning | 140 | Decrease actity cycle by 1h
12 | Customer Adaptation Handling | 3. Production Preparation | 80 | Decrease activity cycle by 1h
13 | Schedule Lines | 2. Material Resource Planning | 60 | Decrease activity cycle by 1h
14 | Planning takts | 1. Capacity Planning | 60 | Must-have to increase capacity to 2000 units
15 | Customer Adaptation Handling | 8. Bus Assembly | 160 | Must-have to increase capacity to 2000 units
16 | Customer Adaptation Handling | 7. In-house Component Sub-assembly | 60 | Decrease activity cycle by 2h
17 | Planning Production Pipeline | 1. Capacity Planning | 80 | Must-have to increase capacity to 2000 units
18 | Direct-deliveries to Production Line | 4. Goods Receiving | 100 | Decrease 1 FTE
19 | Costing | 9. Bus Delivery | 80 | Decrease 1 FTE
20 | Line Routing Preparation | 3. Production Preparation | 120 | Decrease activity cycle by 1h
21 | Invoicing | 9. Bus Delivery | 60 | Decrease 1 FTE
22 | Material Control | 5. Quality Control | 20 | Decrease 1 FTE
23 | Production confirmation | 9. Bus Delivery | 60 | Decrease actity cycle by 1h
24 | Quality Audit | 5. Quality Control | 80 | Decrease actity cycle by 0.5h
25 | Warehouse Good Receiving | 4. Goods Receiving | 40 | Decrease activity cycle by 2h
26 | Just In Sequence | 6. Materials Picking | 80 | Decrease 1 FTE
27 | Production Control | 5. Quality Control | 30 | Decrease actity cycle by 0.5h

## Activity 1 - Business Case
Activity 1
To calculate business case for the project
Project Cost per 1 Bus Unit - As-Is
ID | Activity | Duration (h) | FTE | Worktype | WorkCost | ActvityCost
1 | 1. Capacity Planning | 2 | 2 | White collar | 200 | 800
2 | 2. Material Resource Planning | 4 | 4 | White collar | 200 | 3200
3 | 3. Production Preparation | 6 | 4 | White collar | 200 | 4800
4 | 4. Goods Receving | 10 | 5 | Blue collar | 50 | 2500
5 | 5. Quality Control | 4 | 4 | White collar | 200 | 3200
6 | 6. Materials Picking | 2 | 8 | Blue collar | 50 | 800
7 | 7. In-house Component Sub-assembly | 20 | 8 | Blue collar | 50 | 8000
8 | 8. Bus Assembly | 16 | 48 | Blue collar | 50 | 38400
9 | 9. Bus Delivery | 2 | 4 | White collar | 200 | 1600
63300
Project Cost per 1 Bus Unit - To-Be
ID | Activity | Duration (h) | FTE | Worktype | WorkCost | ActvityCost
1 | 1. Capacity Planning | 2 | 2 | White collar | 200 | 800
2 | 2. Material Resource Planning | 4 | 4 | White collar | 200 | 3200
3 | 3. Production Preparation | 3 | 4 | White collar | 200 | 2400
4 | 4. Goods Receving | 5 | 4 | Blue collar | 50 | 1000
5 | 5. Quality Control | 3 | 3 | White collar | 200 | 1800
6 | 6. Materials Picking | 2 | 8 | Blue collar | 50 | 800
7 | 7. In-house Component Sub-assembly | 16 | 6 | Blue collar | 50 | 4800
8 | 8. Bus Assembly | 16 | 48 | Blue collar | 50 | 38400
9 | 9. Bus Delivery | 1 | 2 | White collar | 200 | 400
53600
Cost saving per 1 unit |  | 9700
to be yearly capacity |  | 2000
Yearly saving |  | 19400000 | Monthly | 1616666.6667 |  | Weekly | 373076.9231 | Daily | 53150.6849
Waterfall deployment (Phased) | Plan | Analyze | Design | Build (Development) | Test | Deploy | Total
Estimate benchmark | 10% | 15% | 15% | 30% | 20% | 10% | 100%
Effort | 620 | 930 | 930 | 1860 | 1240 | 620 | 6200
Cost (300 PLN/H) | [6 empty] | 1860000
Payback |  | 1.1505 | Months

## Activity 2 - Scope
Activity 2
To define project scope
Project Budget As-Is
Waterfall deployment (Phased) | Plan | Analyze | Design | Build (Development) | Test | Deploy
Estimate benchmark | 10% | 15% | 15% | 30% | 20% | 10% |  | Cost
Effort | 800 | 1200 | 1200 | 2400 | 1600 | 800 | 8000 | 300 | 2400000
Project Budget To Be
Waterfall deployment (Phased) | Plan | Analyze | Design | Build (Development) | Test | Deploy
Estimate benchmark | 10% | 15% | 15% | 30% | 20% | 10% |  | Cost
Effort | 620 | 930 | 930 | 1860 | 1240 | 620 | 6200 | 300 | 1860000
Estimated development limited to 2000h
1. Iteration 1 - Must-have and dependent requirements due to must haves
ID | Requirement | Area | Estimated dev (h) | Value added | Prio
6 | Manufacturing Execution Dashboards | 8. Bus Assembly | 280 | Must-have to increase capacity to 2000 units | 1
4 | Just In Sequence | 8. Bus Assembly | 160 | Must-have to increase capacity to 2000 units | 1
15 | Customer Adaptation Handling | 8. Bus Assembly | 160 | Must-have to increase capacity to 2000 units | 1
17 | Planning Production Pipeline | 1. Capacity Planning | 80 | Must-have to increase capacity to 2000 units | 1
19 | Costing | 9. Bus Delivery | 80 | Decrease 1 FTE | 1
24 | Quality Audit | 5. Quality Control | 80 | Decrease actity cycle by 0.5h | 1
14 | Planning takts | 1. Capacity Planning | 60 | Must-have to increase capacity to 2000 units | 1
21 | Invoicing | 9. Bus Delivery | 60 | Decrease 1 FTE | 1
23 | Production confirmation | 9. Bus Delivery | 60 | Decrease actity cycle by 1h | 1
9 | Planning capacity of workstation | 1. Capacity Planning | 30 | Must-have to increase capacity to 2000 units | 1
27 | Production Control | 5. Quality Control | 30 | Decrease actity cycle by 0.5h | 1
22 | Material Control | 5. Quality Control | 20 | Decrease 1 FTE | 1
2 | EDI Communication | 4. Goods Receiving | 120 | Decrease activity cycle by 3h | 2
18 | Direct-deliveries to Production Line | 4. Goods Receiving | 100 | Decrease 1 FTE | 2
1 | Kanban functionality | 6. Materials Picking | 80 | Decrease 1 FTE | 2
5 | Just In Sequence | 7. In-house Component Sub-assembly | 80 | Decrease activity cycle by 2h | 2
7 | Manufacturing Execution Dashboards | 7. In-house Component Sub-assembly | 80 | Decrase 2 FTE | 2
26 | Just In Sequence | 6. Materials Picking | 80 | Decrease 1 FTE | 2
8 | Two-step picking | 6. Materials Picking | 60 | Decrease 1 FTE | 2
16 | Customer Adaptation Handling | 7. In-house Component Sub-assembly | 60 | Decrease activity cycle by 2h | 2
25 | Warehouse Good Receiving | 4. Goods Receiving | 40 | Decrease activity cycle by 2h | 2
10 | Bill Of Material Preparation | 3. Production Preparation | 80 | Decrease activity cycle by 1h | 3
12 | Customer Adaptation Handling | 3. Production Preparation | 80 | Decrease activity cycle by 1h | 3
3 | EDI Communication | 2. Material Resource Planning | 120 | Decrease 1 FTE | 3
11 | Deviations handling | 2. Material Resource Planning | 140 | Decrease actity cycle by 1h | 3
20 | Line Routing Preparation | 3. Production Preparation | 120 | Decrease activity cycle by 1h | 3
13 | Schedule Lines | 2. Material Resource Planning | 60 | Decrease activity cycle by 1h | 3
ID | Requirement | Area | Estimated dev (h) | Value added | Prio
2. Iteration 2 - Most extreme values (lowest priority for Dev and Value are excluded gradually to fit into the budget)
6 | Manufacturing Execution Dashboards | 8. Bus Assembly | 280 | Must-have to increase capacity to 2000 units | 1
4 | Just In Sequence | 8. Bus Assembly | 160 | Must-have to increase capacity to 2000 units | 1
15 | Customer Adaptation Handling | 8. Bus Assembly | 160 | Must-have to increase capacity to 2000 units | 1
17 | Planning Production Pipeline | 1. Capacity Planning | 80 | Must-have to increase capacity to 2000 units | 1
19 | Costing | 9. Bus Delivery | 80 | Decrease 1 FTE | 1
24 | Quality Audit | 5. Quality Control | 80 | Decrease actity cycle by 0.5h | 1
14 | Planning takts | 1. Capacity Planning | 60 | Must-have to increase capacity to 2000 units | 1
21 | Invoicing | 9. Bus Delivery | 60 | Decrease 1 FTE | 1
23 | Production confirmation | 9. Bus Delivery | 60 | Decrease actity cycle by 1h | 1
9 | Planning capacity of workstation | 1. Capacity Planning | 30 | Must-have to increase capacity to 2000 units | 1
27 | Production Control | 5. Quality Control | 30 | Decrease actity cycle by 0.5h | 1
22 | Material Control | 5. Quality Control | 20 | Decrease 1 FTE | 1
2 | EDI Communication | 4. Goods Receiving | 120 | Decrease activity cycle by 3h | 2
18 | Direct-deliveries to Production Line | 4. Goods Receiving | 100 | Decrease 1 FTE | 2
1 | Kanban functionality | 6. Materials Picking | 80 | Decrease 1 FTE | 2
5 | Just In Sequence | 7. In-house Component Sub-assembly | 80 | Decrease activity cycle by 2h | 2
7 | Manufacturing Execution Dashboards | 7. In-house Component Sub-assembly | 80 | Decrase 2 FTE | 2
26 | Just In Sequence | 6. Materials Picking | 80 | Decrease 1 FTE | 2
8 | Two-step picking | 6. Materials Picking | 60 | Decrease 1 FTE | 2
16 | Customer Adaptation Handling | 7. In-house Component Sub-assembly | 60 | Decrease activity cycle by 2h | 2
25 | Warehouse Good Receiving | 4. Goods Receiving | 40 | Decrease activity cycle by 2h | 2
2. Iteration 3 - OUT OF SCOPE
ID | Requirement | Area | Estimated dev (h) | Value added | Prio
17 | Planning Production Pipeline | 1. Capacity Planning | 80 | Must-have to increase capacity to 2000 units | 1
14 | Planning takts | 1. Capacity Planning | 60 | Must-have to increase capacity to 2000 units | 1
9 | Planning capacity of workstation | 1. Capacity Planning | 30 | Must-have to increase capacity to 2000 units | 1
24 | Quality Audit | 5. Quality Control | 80 | Decrease actity cycle by 0.5h | 1
27 | Production Control | 5. Quality Control | 30 | Decrease actity cycle by 0.5h | 1
22 | Material Control | 5. Quality Control | 20 | Decrease 1 FTE | 1
6 | Manufacturing Execution Dashboards | 8. Bus Assembly | 280 | Must-have to increase capacity to 2000 units | 1
4 | Just In Sequence | 8. Bus Assembly | 160 | Must-have to increase capacity to 2000 units | 1
15 | Customer Adaptation Handling | 8. Bus Assembly | 160 | Must-have to increase capacity to 2000 units | 1
19 | Costing | 9. Bus Delivery | 80 | Decrease 1 FTE | 1
21 | Invoicing | 9. Bus Delivery | 60 | Decrease 1 FTE | 1
23 | Production confirmation | 9. Bus Delivery | 60 | Decrease actity cycle by 1h | 1
10 | Bill Of Material Preparation | 3. Production Preparation | 80 | Decrease activity cycle by 1h | 2
12 | Customer Adaptation Handling | 3. Production Preparation | 80 | Decrease activity cycle by 1h | 2
20 | Line Routing Preparation | 3. Production Preparation | 120 | Decrease activity cycle by 1h | 2
2 | EDI Communication | 4. Goods Receiving | 120 | Decrease activity cycle by 3h | 2
18 | Direct-deliveries to Production Line | 4. Goods Receiving | 100 | Decrease 1 FTE | 2
25 | Warehouse Good Receiving | 4. Goods Receiving | 40 | Decrease activity cycle by 2h | 2
5 | Just In Sequence | 7. In-house Component Sub-assembly | 80 | Decrease activity cycle by 2h | 2
7 | Manufacturing Execution Dashboards | 7. In-house Component Sub-assembly | 80 | Decrase 2 FTE | 2
16 | Customer Adaptation Handling | 7. In-house Component Sub-assembly | 60 | Decrease activity cycle by 2h | 2

## Activity 3 - Project Team
Activity 3
To define project team
Waterfall deployment (Phased) | Estimate benchmark | Role
Plan | 10% | PM
Analyze | 15% | BA
Design | 15% | SA
Build (Development) | 30% | D
Test | 20% | T
Deploy | 10% | D
Available IT Roles | Cost [PLN/H]
Project/Test Manager (PM) | 400
Business Analyst (BA) | 250
Solution Architect (SA) | 300
Developer (D) | 300
Tester (T) | 200
Waterfall deployment (Phased) | Plan | Analyze | Design | Build (Development) | Test | Deploy
Estimate benchmark | 10% | 15% | 15% | 30% | 20% | 10%
Project Role | PM | BA | SA | D | T | D
Estimated dev in project (h) | 660 | 990 | 990 | 1980 | 1320 | 660
Assignment duration in weeks | 4 | 7 | 8 | 14 | 5 | 4
FTE | 4.125 | 3.5357 | 3.0938 | 3.5357 | 6.6 | 4.125
IT TEAM
IT role | Number of FTE
Project/Test Manager (PM) | 4
Business Analyst (BA) | 4
Solution Architect (SA) | 3
Developer (D) | 4
Tester (T) | 7

## Activity 4 Schedule Development
Activity 4
Replanned schedule:
Design Phase Plan |  |  |  |  | w01 | w02 | w03 | w04 | w05 | w06 | w07 | w08 | w09 | w10 | w11 | w12 | w13 | w14 | w15 | w16 | w17
Task Name | Duration | Duration | who | Priority
Just In Sequence | 160 | 80 | BA1 | 1 | w01: 40; w02: 40
Just In Sequence | 80 | 40 | BA1 | 1 | w03: 40
Manufacturing Execution Dashboards | 280 | 140 | BA4 | 1 | w01: 40; w02: 40; w03: 40; w04: 20
Planning capacity of workstation | 30 | 15 | BA2 | 1 | w01: 15
Planning takts | 60 | 30 | BA2 | 1 | w01: 25; w07: 5
Customer Adaptation Handling | 160 | 80 | BA2 | 1 | w07: 35; w08: 40; w09: 5
Planning Production Pipeline | 80 | 40 | BA2 | 1 | w09: 35; w10: 5
Costing | 80 | 40 | BA2 | 1 | w10: 35; w11: 5
Invoicing | 60 | 30 | BA2 | 1 | w11: 30
Material Control | 20 | 10 | BA1 | 1 | w04: 10
Production confirmation | 60 | 30 | BA3 | 1 | w01: 30
Quality Audit | 80 | 40 | BA3 | 1 | w01: 10; w02: 30
Just In Sequence | 80 | 40 | BA3 | 1 | w02: 10; w03: 30
Production Control | 30 | 15 | BA1 | 1 | w07: 10; w08: 5
Manufacturing Execution Dashboards | 80 | 40 | BA3 | 1 | w03: 10; w04: 30
Customer Adaptation Handling | 80 | 40 | BA3 | 1 | w04: 10; w07: 30
Warehouse Good Receiving | 40 | 20 | BA3 | 2 | w07: 10; w08: 10
Two-step picking | 60 | 30 | BA3 | 2 | w08: 30
Schedule Lines | 60 | 30 | BA3 | 2 | w09: 30
Customer Adaptation Handling | 60 | 30 | BA4 | 2 | w04: 20; w07: 10
Direct-deliveries to Production Line | 100 | 50 | BA4 | 2 | w07: 30; w08: 10
Bill Of Material Preparation | 80 | 40 | BA4 | 2 | w08: 30; w09: 10
Line Routing Preparation | 120 | 60 | BA1 | 2 | w04: 30; w07: 30
515
|  |  | BA1 | 260
|  |  | BA2 | 250
|  |  | BA3 | 270
|  |  | BA4 | 260

## Status Report (hidden)
Project status overview
Overall Status | Scope & Deliverables | Schedule | Budget Follow Up | Resources | Issues & Risks
Current Phase:
Next Gate:
Date of Next Gate Meeting:
Overall status
Scope & Deliverables

## Sheet1
| zadanie 1 | zadanie 2 | zadanie 3 | zadanie 4 | zadanie 5 | suma punktow
grupa
1 | [5 empty] | 0
2 | [5 empty] | 0
3 | [5 empty] | 0
4 | [5 empty] | 0
5 | [5 empty] | 0
6 | [5 empty] | 0
7 | [5 empty] | 0
8 | [5 empty] | 0
9 | [5 empty] | 0
10 | [5 empty] | 0
11 | [5 empty] | 0
12 | [5 empty] | 0
13 | [5 empty] | 0
14 | [5 empty] | 0
15 | [5 empty] | 0
16 | [5 empty] | 0